## Tasks
Group (Block) | Name | Description | Task ID | Type | Owner Role | Side | Tool of Record | Scope | Depends On | Status | Duration | Notes | Assignee | External Owner
Note on A1: Use a group CODE: B1, B2, B3, B4, B5a, B5b, B6, B6.5, B7. See Legend sheet. Codes or canonical titles accepted; merged labels (e.g. '5a&5b') are rejected.
Note on D1: Unique, never reused. This is the cross-system join key (Monday <-> Jira).
Note on F1: Multi-select: comma-separate multiple roles (e.g. 'Implementation Lead, Post-Sales SE'). A slash is part of a label (Customer-CX/Ops is one role). Allowed: AE, Callvu Dev, Callvu-Exec, Customer-Business, Customer-Compliance, Customer-CX/Ops, Customer-Exec, Customer-PM, Customer-Tech, Implementation Lead, Post-Sales SE, Owner per upstream block
Note on J1: Comma-separated Task IDs this task depends on. Leave blank if none.
Note on L1: Business days (number). Milestones (Type = gate or sign off) must be 0.

## Legend
Group (Block) codes — use the CODE in the Tasks sheet
Code | Canonical title
B1 | Block 1 · Implementation Scoping
B2 | Block 2 · Technical & Compliance
B3 | Block 3 · Provisioning & Foundations
B4 | Block 4 · Integration & Wiring
B5a | Block 5a · Workflow Build
B5b | Block 5b · UI Build
B6 | Block 6 · Validation
B6.5 | Block 6.5 · Remediation
B7 | Block 7 · UAT & Go Live
Controlled vocabularies — allowed values per column
Column | Allowed values
Type | gate, sign off, task
Side | Callvu, customer, joint
Tool of Record | Monday, Jira
Scope | once, per use case, variable
Status | not started, done
Owner Role | AE, Callvu Dev, Callvu-Exec, Customer-Business, Customer-Compliance, Customer-CX/Ops, Customer-Exec, Customer-PM, Customer-Tech, Implementation Lead, Post-Sales SE, Owner per upstream block (multi-select: comma-separated, slash is literal)
Notes
• Every data row in Tasks must be a real task with a Task ID. There are no section-header rows.
• Duration is in business days. Milestones (Type = gate or sign off) carry Duration 0.
• Do not author Start or Due dates. The scheduler computes the timeline from kickoff + durations + dependencies.
• Depends On uses Task IDs, comma-separated.
Optional columns (Cycle 2) — leave blank if unused
Column | How to fill
Assignee | A person's email (e.g. name@company.com). Blank -> default assignee. Resolved to a Jira account at Build.
External Owner | A client-side owner with no Jira account, format 'Name <email>' (email optional). Display-only; does not create a ticket.

## Lists (hidden)
Group (Block) | Type | Side | Tool of Record | Scope | Status | Owner Role
B1 | gate | Callvu | Monday | once | not started | AE
B2 | sign off | customer | Jira | per use case | done | Callvu Dev
B3 | task | joint |  | variable |  | Callvu-Exec
B4 | [5 empty] | Customer-Business
B5a | [5 empty] | Customer-Compliance
B5b | [5 empty] | Customer-CX/Ops
B6 | [5 empty] | Customer-Exec
B6.5 | [5 empty] | Customer-PM
B7 | [5 empty] | Customer-Tech
Implementation Lead
Post-Sales SE
Owner per upstream block